## Project Plan Template
ROS | Restaurant Order System
TOTAL TASKS | 11 |  | Duration | 13 |  | Overall Progress
Completed | 4 |  | Project Start | 2023-04-20
In progress | 2 |  | Project End | 2023-05-02 |  | 23.68%
Not Started | 13
76.32%
Tasks | Responsible | Start Date | End Date | Progress | Status | Duration | Completed | Pending
Organizational |  | 2023-04-20 | 2023-04-28 | 100% | Completed
Creating Group & Allocating Jobs | AJ, DK, RY, NW, MP | 2023-04-20 | 2023-04-21 | 100% | Completed | 2 | 2 | 0
Github Repository Setup | AJ | 2023-04-27 | 2023-04-28 | 100% | Completed | 2 | 2 | 0
Creation of Project Plan | AJ, NW | 2023-04-27 | 2023-05-02 | 50% | In progress | 6 | 3 | 3
Creation of Attendance Sheet | AJ | 2023-04-27 | 2023-04-28 | 100% | Completed | 2 | 2 | 0
Setting up the Database |  |  |  | 0% | In progress | 1 | 0 | 1
Defining of requirements |  |  |  | 0% | Not Started | 1 | 0 | 1
Designing of Schema |  |  |  | 0% | Not Started | 1 | 0 | 1
Creation of DB & Tables |  |  |  | 0% | Not Started | 1 | 0 | 1
Population of database |  |  |  | 0% | Not Started | 1 | 0 | 1
Adding of security features |  |  |  | 0% | Not Started | 1 | 0 | 1
|  |  |  | 0% | Not Started
|  |  |  | 0% | Not Started
|  |  |  | 0% | Not Started
|  |  |  | 0% | Not Started
|  |  |  | 0% | Not Started
|  |  |  | 0% | Not Started
|  |  |  | 0% | Not Started
|  |  |  | 0% | Not Started

## Project Team
Symbol | Last name | Name
AJ | Jamil | Arham
DK | Kammos | Dennis
RY | Yampang | Roger
NW | Wulandari | Natasya
MP | Pewny | Maximilian